## Defects & Blocked
Test Case ID | Testing Suite | Module | Test Name | Priority | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Duration (ms) | Status | Failure Reason | Evidence Location | Defect Reference
APP-341 | Android - Appium | Hardware Biometrics & Sensor Checks | Hardware Biometrics & Sensor Checks Check #1: Initial render and UI state of Hardware Biometrics & Sensor Checks | Low | APK com.example.best3 compiled; UiAutomator2 driver connected | 1. Launch MainActivity 2. Navigate to Hardware Biometrics & Sensor Checks 3. Trigger target Compose interaction 4. Verify element states and assertions | Device: Google Pixel 8 Emulator (API 34), Package: com.example.best3 | Requires physical biometric sensor hardware | Blocked - Hardware fingerprint/face sensor not available on CI headless emulator | 0 | Blocked | Hardware biometric fingerprint sensor unavailable on virtual emulator environment | N/A | DEF-BIO-001
APP-342 | Android - Appium | Hardware Biometrics & Sensor Checks | Hardware Biometrics & Sensor Checks Check #2: State preservation on configuration change in Hardware Biometrics & Sensor Checks | Low | APK com.example.best3 compiled; UiAutomator2 driver connected | 1. Launch MainActivity 2. Navigate to Hardware Biometrics & Sensor Checks 3. Trigger target Compose interaction 4. Verify element states and assertions | Device: Google Pixel 8 Emulator (API 34), Package: com.example.best3 | Requires physical biometric sensor hardware | Blocked - Hardware fingerprint/face sensor not available on CI headless emulator | 0 | Blocked | Hardware biometric fingerprint sensor unavailable on virtual emulator environment | N/A | DEF-BIO-001
APP-343 | Android - Appium | Hardware Biometrics & Sensor Checks | Hardware Biometrics & Sensor Checks Check #3: Data binding and Compose recomposition efficiency in Hardware Biometrics & Sensor Checks | Low | APK com.example.best3 compiled; UiAutomator2 driver connected | 1. Launch MainActivity 2. Navigate to Hardware Biometrics & Sensor Checks 3. Trigger target Compose interaction 4. Verify element states and assertions | Device: Google Pixel 8 Emulator (API 34), Package: com.example.best3 | Requires physical biometric sensor hardware | Blocked - Hardware fingerprint/face sensor not available on CI headless emulator | 0 | Blocked | Hardware biometric fingerprint sensor unavailable on virtual emulator environment | N/A | DEF-BIO-001
APP-344 | Android - Appium | Hardware Biometrics & Sensor Checks | Hardware Biometrics & Sensor Checks Check #4: Error recovery and fallback UI handling in Hardware Biometrics & Sensor Checks | Low | APK com.example.best3 compiled; UiAutomator2 driver connected | 1. Launch MainActivity 2. Navigate to Hardware Biometrics & Sensor Checks 3. Trigger target Compose interaction 4. Verify element states and assertions | Device: Google Pixel 8 Emulator (API 34), Package: com.example.best3 | Requires physical biometric sensor hardware | Blocked - Hardware fingerprint/face sensor not available on CI headless emulator | 0 | Blocked | Hardware biometric fingerprint sensor unavailable on virtual emulator environment | N/A | DEF-BIO-001
APP-345 | Android - Appium | Hardware Biometrics & Sensor Checks | Hardware Biometrics & Sensor Checks Check #5: Accessibility semantics and contentDescription in Hardware Biometrics & Sensor Checks | Low | APK com.example.best3 compiled; UiAutomator2 driver connected | 1. Launch MainActivity 2. Navigate to Hardware Biometrics & Sensor Checks 3. Trigger target Compose interaction 4. Verify element states and assertions | Device: Google Pixel 8 Emulator (API 34), Package: com.example.best3 | Requires physical biometric sensor hardware | Blocked - Hardware fingerprint/face sensor not available on CI headless emulator | 0 | Blocked | Hardware biometric fingerprint sensor unavailable on virtual emulator environment | N/A | DEF-BIO-001
APP-346 | Android - Appium | Hardware Biometrics & Sensor Checks | Hardware Biometrics & Sensor Checks Check #6: Hardware Biometrics & Sensor Checks component action and lifecycle assertion #6 | Low | APK com.example.best3 compiled; UiAutomator2 driver connected | 1. Launch MainActivity 2. Navigate to Hardware Biometrics & Sensor Checks 3. Trigger target Compose interaction 4. Verify element states and assertions | Device: Google Pixel 8 Emulator (API 34), Package: com.example.best3 | Requires physical biometric sensor hardware | Blocked - Hardware fingerprint/face sensor not available on CI headless emulator | 0 | Blocked | Hardware biometric fingerprint sensor unavailable on virtual emulator environment | N/A | DEF-BIO-001
APP-347 | Android - Appium | Hardware Biometrics & Sensor Checks | Hardware Biometrics & Sensor Checks Check #7: Hardware Biometrics & Sensor Checks component action and lifecycle assertion #7 | Low | APK com.example.best3 compiled; UiAutomator2 driver connected | 1. Launch MainActivity 2. Navigate to Hardware Biometrics & Sensor Checks 3. Trigger target Compose interaction 4. Verify element states and assertions | Device: Google Pixel 8 Emulator (API 34), Package: com.example.best3 | Requires physical biometric sensor hardware | Blocked - Hardware fingerprint/face sensor not available on CI headless emulator | 0 | Blocked | Hardware biometric fingerprint sensor unavailable on virtual emulator environment | N/A | DEF-BIO-001
APP-348 | Android - Appium | Hardware Biometrics & Sensor Checks | Hardware Biometrics & Sensor Checks Check #8: Hardware Biometrics & Sensor Checks component action and lifecycle assertion #8 | Low | APK com.example.best3 compiled; UiAutomator2 driver connected | 1. Launch MainActivity 2. Navigate to Hardware Biometrics & Sensor Checks 3. Trigger target Compose interaction 4. Verify element states and assertions | Device: Google Pixel 8 Emulator (API 34), Package: com.example.best3 | Requires physical biometric sensor hardware | Blocked - Hardware fingerprint/face sensor not available on CI headless emulator | 0 | Blocked | Hardware biometric fingerprint sensor unavailable on virtual emulator environment | N/A | DEF-BIO-001
APP-349 | Android - Appium | Hardware Biometrics & Sensor Checks | Hardware Biometrics & Sensor Checks Check #9: Hardware Biometrics & Sensor Checks component action and lifecycle assertion #9 | Low | APK com.example.best3 compiled; UiAutomator2 driver connected | 1. Launch MainActivity 2. Navigate to Hardware Biometrics & Sensor Checks 3. Trigger target Compose interaction 4. Verify element states and assertions | Device: Google Pixel 8 Emulator (API 34), Package: com.example.best3 | Requires physical biometric sensor hardware | Blocked - Hardware fingerprint/face sensor not available on CI headless emulator | 0 | Blocked | Hardware biometric fingerprint sensor unavailable on virtual emulator environment | N/A | DEF-BIO-001
APP-350 | Android - Appium | Hardware Biometrics & Sensor Checks | Hardware Biometrics & Sensor Checks Check #10: Hardware Biometrics & Sensor Checks component action and lifecycle assertion #10 | Low | APK com.example.best3 compiled; UiAutomator2 driver connected | 1. Launch MainActivity 2. Navigate to Hardware Biometrics & Sensor Checks 3. Trigger target Compose interaction 4. Verify element states and assertions | Device: Google Pixel 8 Emulator (API 34), Package: com.example.best3 | Requires physical biometric sensor hardware | Blocked - Hardware fingerprint/face sensor not available on CI headless emulator | 0 | Blocked | Hardware biometric fingerprint sensor unavailable on virtual emulator environment | N/A | DEF-BIO-001
PERF-226 | API Performance | Uncapped Production DoS Stress Profile | Uncapped Production DoS Stress Profile Metric #1: Target endpoint response latency under Uncapped Production DoS Stress Profile | Critical | k6 performance harness running with 100 Virtual Users for 60 seconds | 1. Initialize k6 VU workers 2. Dispatch HTTP requests continuously 3. Record latencies and response codes 4. Compute statistics | VUs: 100, Duration: 60s, Target: Approved Endpoints (/, /shop, /ai-stylist, /fabric-encyclopedia) | Requires explicit executive authorization for destructive volumetric attack | Blocked - Volumetric DoS / Uncapped stress testing against live host blocked by security policy | 0 | Blocked | Safety Policy Gate: Destructive 1000+ VU DoS / Stress tests require explicit sign-off | N/A | DEF-PERF-BLOCKED
PERF-227 | API Performance | Uncapped Production DoS Stress Profile | Uncapped Production DoS Stress Profile Metric #2: Error rate threshold compliance (<1%) under Uncapped Production DoS Stress Profile | Critical | k6 performance harness running with 100 Virtual Users for 60 seconds | 1. Initialize k6 VU workers 2. Dispatch HTTP requests continuously 3. Record latencies and response codes 4. Compute statistics | VUs: 100, Duration: 60s, Target: Approved Endpoints (/, /shop, /ai-stylist, /fabric-encyclopedia) | Requires explicit executive authorization for destructive volumetric attack | Blocked - Volumetric DoS / Uncapped stress testing against live host blocked by security policy | 0 | Blocked | Safety Policy Gate: Destructive 1000+ VU DoS / Stress tests require explicit sign-off | N/A | DEF-PERF-BLOCKED
PERF-228 | API Performance | Uncapped Production DoS Stress Profile | Uncapped Production DoS Stress Profile Metric #3: RPS throughput consistency over 60 seconds | Critical | k6 performance harness running with 100 Virtual Users for 60 seconds | 1. Initialize k6 VU workers 2. Dispatch HTTP requests continuously 3. Record latencies and response codes 4. Compute statistics | VUs: 100, Duration: 60s, Target: Approved Endpoints (/, /shop, /ai-stylist, /fabric-encyclopedia) | Requires explicit executive authorization for destructive volumetric attack | Blocked - Volumetric DoS / Uncapped stress testing against live host blocked by security policy | 0 | Blocked | Safety Policy Gate: Destructive 1000+ VU DoS / Stress tests require explicit sign-off | N/A | DEF-PERF-BLOCKED
PERF-229 | API Performance | Uncapped Production DoS Stress Profile | Uncapped Production DoS Stress Profile Metric #4: Connection pooling and HTTP keep-alive reuse | Critical | k6 performance harness running with 100 Virtual Users for 60 seconds | 1. Initialize k6 VU workers 2. Dispatch HTTP requests continuously 3. Record latencies and response codes 4. Compute statistics | VUs: 100, Duration: 60s, Target: Approved Endpoints (/, /shop, /ai-stylist, /fabric-encyclopedia) | Requires explicit executive authorization for destructive volumetric attack | Blocked - Volumetric DoS / Uncapped stress testing against live host blocked by security policy | 0 | Blocked | Safety Policy Gate: Destructive 1000+ VU DoS / Stress tests require explicit sign-off | N/A | DEF-PERF-BLOCKED
PERF-230 | API Performance | Uncapped Production DoS Stress Profile | Uncapped Production DoS Stress Profile Metric #5: Uncapped Production DoS Stress Profile load benchmark case #5 | Critical | k6 performance harness running with 100 Virtual Users for 60 seconds | 1. Initialize k6 VU workers 2. Dispatch HTTP requests continuously 3. Record latencies and response codes 4. Compute statistics | VUs: 100, Duration: 60s, Target: Approved Endpoints (/, /shop, /ai-stylist, /fabric-encyclopedia) | Requires explicit executive authorization for destructive volumetric attack | Blocked - Volumetric DoS / Uncapped stress testing against live host blocked by security policy | 0 | Blocked | Safety Policy Gate: Destructive 1000+ VU DoS / Stress tests require explicit sign-off | N/A | DEF-PERF-BLOCKED
PERF-231 | API Performance | Uncapped Production DoS Stress Profile | Uncapped Production DoS Stress Profile Metric #6: Uncapped Production DoS Stress Profile load benchmark case #6 | Critical | k6 performance harness running with 100 Virtual Users for 60 seconds | 1. Initialize k6 VU workers 2. Dispatch HTTP requests continuously 3. Record latencies and response codes 4. Compute statistics | VUs: 100, Duration: 60s, Target: Approved Endpoints (/, /shop, /ai-stylist, /fabric-encyclopedia) | Requires explicit executive authorization for destructive volumetric attack | Blocked - Volumetric DoS / Uncapped stress testing against live host blocked by security policy | 0 | Blocked | Safety Policy Gate: Destructive 1000+ VU DoS / Stress tests require explicit sign-off | N/A | DEF-PERF-BLOCKED
PERF-232 | API Performance | Uncapped Production DoS Stress Profile | Uncapped Production DoS Stress Profile Metric #7: Uncapped Production DoS Stress Profile load benchmark case #7 | Critical | k6 performance harness running with 100 Virtual Users for 60 seconds | 1. Initialize k6 VU workers 2. Dispatch HTTP requests continuously 3. Record latencies and response codes 4. Compute statistics | VUs: 100, Duration: 60s, Target: Approved Endpoints (/, /shop, /ai-stylist, /fabric-encyclopedia) | Requires explicit executive authorization for destructive volumetric attack | Blocked - Volumetric DoS / Uncapped stress testing against live host blocked by security policy | 0 | Blocked | Safety Policy Gate: Destructive 1000+ VU DoS / Stress tests require explicit sign-off | N/A | DEF-PERF-BLOCKED
PERF-233 | API Performance | Uncapped Production DoS Stress Profile | Uncapped Production DoS Stress Profile Metric #8: Uncapped Production DoS Stress Profile load benchmark case #8 | Critical | k6 performance harness running with 100 Virtual Users for 60 seconds | 1. Initialize k6 VU workers 2. Dispatch HTTP requests continuously 3. Record latencies and response codes 4. Compute statistics | VUs: 100, Duration: 60s, Target: Approved Endpoints (/, /shop, /ai-stylist, /fabric-encyclopedia) | Requires explicit executive authorization for destructive volumetric attack | Blocked - Volumetric DoS / Uncapped stress testing against live host blocked by security policy | 0 | Blocked | Safety Policy Gate: Destructive 1000+ VU DoS / Stress tests require explicit sign-off | N/A | DEF-PERF-BLOCKED
PERF-234 | API Performance | Uncapped Production DoS Stress Profile | Uncapped Production DoS Stress Profile Metric #9: Uncapped Production DoS Stress Profile load benchmark case #9 | Critical | k6 performance harness running with 100 Virtual Users for 60 seconds | 1. Initialize k6 VU workers 2. Dispatch HTTP requests continuously 3. Record latencies and response codes 4. Compute statistics | VUs: 100, Duration: 60s, Target: Approved Endpoints (/, /shop, /ai-stylist, /fabric-encyclopedia) | Requires explicit executive authorization for destructive volumetric attack | Blocked - Volumetric DoS / Uncapped stress testing against live host blocked by security policy | 0 | Blocked | Safety Policy Gate: Destructive 1000+ VU DoS / Stress tests require explicit sign-off | N/A | DEF-PERF-BLOCKED
PERF-235 | API Performance | Uncapped Production DoS Stress Profile | Uncapped Production DoS Stress Profile Metric #10: Uncapped Production DoS Stress Profile load benchmark case #10 | Critical | k6 performance harness running with 100 Virtual Users for 60 seconds | 1. Initialize k6 VU workers 2. Dispatch HTTP requests continuously 3. Record latencies and response codes 4. Compute statistics | VUs: 100, Duration: 60s, Target: Approved Endpoints (/, /shop, /ai-stylist, /fabric-encyclopedia) | Requires explicit executive authorization for destructive volumetric attack | Blocked - Volumetric DoS / Uncapped stress testing against live host blocked by security policy | 0 | Blocked | Safety Policy Gate: Destructive 1000+ VU DoS / Stress tests require explicit sign-off | N/A | DEF-PERF-BLOCKED
PERF-236 | API Performance | Uncapped Production DoS Stress Profile | Uncapped Production DoS Stress Profile Metric #11: Uncapped Production DoS Stress Profile load benchmark case #11 | Critical | k6 performance harness running with 100 Virtual Users for 60 seconds | 1. Initialize k6 VU workers 2. Dispatch HTTP requests continuously 3. Record latencies and response codes 4. Compute statistics | VUs: 100, Duration: 60s, Target: Approved Endpoints (/, /shop, /ai-stylist, /fabric-encyclopedia) | Requires explicit executive authorization for destructive volumetric attack | Blocked - Volumetric DoS / Uncapped stress testing against live host blocked by security policy | 0 | Blocked | Safety Policy Gate: Destructive 1000+ VU DoS / Stress tests require explicit sign-off | N/A | DEF-PERF-BLOCKED
PERF-237 | API Performance | Uncapped Production DoS Stress Profile | Uncapped Production DoS Stress Profile Metric #12: Uncapped Production DoS Stress Profile load benchmark case #12 | Critical | k6 performance harness running with 100 Virtual Users for 60 seconds | 1. Initialize k6 VU workers 2. Dispatch HTTP requests continuously 3. Record latencies and response codes 4. Compute statistics | VUs: 100, Duration: 60s, Target: Approved Endpoints (/, /shop, /ai-stylist, /fabric-encyclopedia) | Requires explicit executive authorization for destructive volumetric attack | Blocked - Volumetric DoS / Uncapped stress testing against live host blocked by security policy | 0 | Blocked | Safety Policy Gate: Destructive 1000+ VU DoS / Stress tests require explicit sign-off | N/A | DEF-PERF-BLOCKED
PERF-238 | API Performance | Uncapped Production DoS Stress Profile | Uncapped Production DoS Stress Profile Metric #13: Uncapped Production DoS Stress Profile load benchmark case #13 | Critical | k6 performance harness running with 100 Virtual Users for 60 seconds | 1. Initialize k6 VU workers 2. Dispatch HTTP requests continuously 3. Record latencies and response codes 4. Compute statistics | VUs: 100, Duration: 60s, Target: Approved Endpoints (/, /shop, /ai-stylist, /fabric-encyclopedia) | Requires explicit executive authorization for destructive volumetric attack | Blocked - Volumetric DoS / Uncapped stress testing against live host blocked by security policy | 0 | Blocked | Safety Policy Gate: Destructive 1000+ VU DoS / Stress tests require explicit sign-off | N/A | DEF-PERF-BLOCKED
PERF-239 | API Performance | Uncapped Production DoS Stress Profile | Uncapped Production DoS Stress Profile Metric #14: Uncapped Production DoS Stress Profile load benchmark case #14 | Critical | k6 performance harness running with 100 Virtual Users for 60 seconds | 1. Initialize k6 VU workers 2. Dispatch HTTP requests continuously 3. Record latencies and response codes 4. Compute statistics | VUs: 100, Duration: 60s, Target: Approved Endpoints (/, /shop, /ai-stylist, /fabric-encyclopedia) | Requires explicit executive authorization for destructive volumetric attack | Blocked - Volumetric DoS / Uncapped stress testing against live host blocked by security policy | 0 | Blocked | Safety Policy Gate: Destructive 1000+ VU DoS / Stress tests require explicit sign-off | N/A | DEF-PERF-BLOCKED
PERF-240 | API Performance | Uncapped Production DoS Stress Profile | Uncapped Production DoS Stress Profile Metric #15: Uncapped Production DoS Stress Profile load benchmark case #15 | Critical | k6 performance harness running with 100 Virtual Users for 60 seconds | 1. Initialize k6 VU workers 2. Dispatch HTTP requests continuously 3. Record latencies and response codes 4. Compute statistics | VUs: 100, Duration: 60s, Target: Approved Endpoints (/, /shop, /ai-stylist, /fabric-encyclopedia) | Requires explicit executive authorization for destructive volumetric attack | Blocked - Volumetric DoS / Uncapped stress testing against live host blocked by security policy | 0 | Blocked | Safety Policy Gate: Destructive 1000+ VU DoS / Stress tests require explicit sign-off | N/A | DEF-PERF-BLOCKED
PERF-241 | API Performance | Uncapped Production DoS Stress Profile | Uncapped Production DoS Stress Profile Metric #16: Uncapped Production DoS Stress Profile load benchmark case #16 | Critical | k6 performance harness running with 100 Virtual Users for 60 seconds | 1. Initialize k6 VU workers 2. Dispatch HTTP requests continuously 3. Record latencies and response codes 4. Compute statistics | VUs: 100, Duration: 60s, Target: Approved Endpoints (/, /shop, /ai-stylist, /fabric-encyclopedia) | Requires explicit executive authorization for destructive volumetric attack | Blocked - Volumetric DoS / Uncapped stress testing against live host blocked by security policy | 0 | Blocked | Safety Policy Gate: Destructive 1000+ VU DoS / Stress tests require explicit sign-off | N/A | DEF-PERF-BLOCKED
PERF-242 | API Performance | Uncapped Production DoS Stress Profile | Uncapped Production DoS Stress Profile Metric #17: Uncapped Production DoS Stress Profile load benchmark case #17 | Critical | k6 performance harness running with 100 Virtual Users for 60 seconds | 1. Initialize k6 VU workers 2. Dispatch HTTP requests continuously 3. Record latencies and response codes 4. Compute statistics | VUs: 100, Duration: 60s, Target: Approved Endpoints (/, /shop, /ai-stylist, /fabric-encyclopedia) | Requires explicit executive authorization for destructive volumetric attack | Blocked - Volumetric DoS / Uncapped stress testing against live host blocked by security policy | 0 | Blocked | Safety Policy Gate: Destructive 1000+ VU DoS / Stress tests require explicit sign-off | N/A | DEF-PERF-BLOCKED
PERF-243 | API Performance | Uncapped Production DoS Stress Profile | Uncapped Production DoS Stress Profile Metric #18: Uncapped Production DoS Stress Profile load benchmark case #18 | Critical | k6 performance harness running with 100 Virtual Users for 60 seconds | 1. Initialize k6 VU workers 2. Dispatch HTTP requests continuously 3. Record latencies and response codes 4. Compute statistics | VUs: 100, Duration: 60s, Target: Approved Endpoints (/, /shop, /ai-stylist, /fabric-encyclopedia) | Requires explicit executive authorization for destructive volumetric attack | Blocked - Volumetric DoS / Uncapped stress testing against live host blocked by security policy | 0 | Blocked | Safety Policy Gate: Destructive 1000+ VU DoS / Stress tests require explicit sign-off | N/A | DEF-PERF-BLOCKED
PERF-244 | API Performance | Uncapped Production DoS Stress Profile | Uncapped Production DoS Stress Profile Metric #19: Uncapped Production DoS Stress Profile load benchmark case #19 | Critical | k6 performance harness running with 100 Virtual Users for 60 seconds | 1. Initialize k6 VU workers 2. Dispatch HTTP requests continuously 3. Record latencies and response codes 4. Compute statistics | VUs: 100, Duration: 60s, Target: Approved Endpoints (/, /shop, /ai-stylist, /fabric-encyclopedia) | Requires explicit executive authorization for destructive volumetric attack | Blocked - Volumetric DoS / Uncapped stress testing against live host blocked by security policy | 0 | Blocked | Safety Policy Gate: Destructive 1000+ VU DoS / Stress tests require explicit sign-off | N/A | DEF-PERF-BLOCKED
PERF-245 | API Performance | Uncapped Production DoS Stress Profile | Uncapped Production DoS Stress Profile Metric #20: Uncapped Production DoS Stress Profile load benchmark case #20 | Critical | k6 performance harness running with 100 Virtual Users for 60 seconds | 1. Initialize k6 VU workers 2. Dispatch HTTP requests continuously 3. Record latencies and response codes 4. Compute statistics | VUs: 100, Duration: 60s, Target: Approved Endpoints (/, /shop, /ai-stylist, /fabric-encyclopedia) | Requires explicit executive authorization for destructive volumetric attack | Blocked - Volumetric DoS / Uncapped stress testing against live host blocked by security policy | 0 | Blocked | Safety Policy Gate: Destructive 1000+ VU DoS / Stress tests require explicit sign-off | N/A | DEF-PERF-BLOCKED
PERF-246 | API Performance | Uncapped Production DoS Stress Profile | Uncapped Production DoS Stress Profile Metric #21: Uncapped Production DoS Stress Profile load benchmark case #21 | Critical | k6 performance harness running with 100 Virtual Users for 60 seconds | 1. Initialize k6 VU workers 2. Dispatch HTTP requests continuously 3. Record latencies and response codes 4. Compute statistics | VUs: 100, Duration: 60s, Target: Approved Endpoints (/, /shop, /ai-stylist, /fabric-encyclopedia) | Requires explicit executive authorization for destructive volumetric attack | Blocked - Volumetric DoS / Uncapped stress testing against live host blocked by security policy | 0 | Blocked | Safety Policy Gate: Destructive 1000+ VU DoS / Stress tests require explicit sign-off | N/A | DEF-PERF-BLOCKED
PERF-247 | API Performance | Uncapped Production DoS Stress Profile | Uncapped Production DoS Stress Profile Metric #22: Uncapped Production DoS Stress Profile load benchmark case #22 | Critical | k6 performance harness running with 100 Virtual Users for 60 seconds | 1. Initialize k6 VU workers 2. Dispatch HTTP requests continuously 3. Record latencies and response codes 4. Compute statistics | VUs: 100, Duration: 60s, Target: Approved Endpoints (/, /shop, /ai-stylist, /fabric-encyclopedia) | Requires explicit executive authorization for destructive volumetric attack | Blocked - Volumetric DoS / Uncapped stress testing against live host blocked by security policy | 0 | Blocked | Safety Policy Gate: Destructive 1000+ VU DoS / Stress tests require explicit sign-off | N/A | DEF-PERF-BLOCKED
PERF-248 | API Performance | Uncapped Production DoS Stress Profile | Uncapped Production DoS Stress Profile Metric #23: Uncapped Production DoS Stress Profile load benchmark case #23 | Critical | k6 performance harness running with 100 Virtual Users for 60 seconds | 1. Initialize k6 VU workers 2. Dispatch HTTP requests continuously 3. Record latencies and response codes 4. Compute statistics | VUs: 100, Duration: 60s, Target: Approved Endpoints (/, /shop, /ai-stylist, /fabric-encyclopedia) | Requires explicit executive authorization for destructive volumetric attack | Blocked - Volumetric DoS / Uncapped stress testing against live host blocked by security policy | 0 | Blocked | Safety Policy Gate: Destructive 1000+ VU DoS / Stress tests require explicit sign-off | N/A | DEF-PERF-BLOCKED
PERF-249 | API Performance | Uncapped Production DoS Stress Profile | Uncapped Production DoS Stress Profile Metric #24: Uncapped Production DoS Stress Profile load benchmark case #24 | Critical | k6 performance harness running with 100 Virtual Users for 60 seconds | 1. Initialize k6 VU workers 2. Dispatch HTTP requests continuously 3. Record latencies and response codes 4. Compute statistics | VUs: 100, Duration: 60s, Target: Approved Endpoints (/, /shop, /ai-stylist, /fabric-encyclopedia) | Requires explicit executive authorization for destructive volumetric attack | Blocked - Volumetric DoS / Uncapped stress testing against live host blocked by security policy | 0 | Blocked | Safety Policy Gate: Destructive 1000+ VU DoS / Stress tests require explicit sign-off | N/A | DEF-PERF-BLOCKED
PERF-250 | API Performance | Uncapped Production DoS Stress Profile | Uncapped Production DoS Stress Profile Metric #25: Uncapped Production DoS Stress Profile load benchmark case #25 | Critical | k6 performance harness running with 100 Virtual Users for 60 seconds | 1. Initialize k6 VU workers 2. Dispatch HTTP requests continuously 3. Record latencies and response codes 4. Compute statistics | VUs: 100, Duration: 60s, Target: Approved Endpoints (/, /shop, /ai-stylist, /fabric-encyclopedia) | Requires explicit executive authorization for destructive volumetric attack | Blocked - Volumetric DoS / Uncapped stress testing against live host blocked by security policy | 0 | Blocked | Safety Policy Gate: Destructive 1000+ VU DoS / Stress tests require explicit sign-off | N/A | DEF-PERF-BLOCKED